## Drawing Register
MicroStation Distribution Design Package — Drawing Register
Drawing No. | Drawing Title | Discipline | Status | Revision | DGN Complete? | PDF Exported? | PDF File Name | Last Updated | Notes
E-000 | Cover Sheet and Drawing Index | General | Complete | 0 | Yes | Yes | E-000-cover-sheet.pdf | 2026-06-10 | Cover sheet and drawing index
E-101 | Existing Conditions Plan | Electrical/Civil | Complete | 0 | Yes | Yes | E-101-existing-conditions-plan.pdf | 2026-06-10 | Existing road, sidewalk, property, transformer, building, pole
E-102 | Proposed Electrical-Civil Plan | Electrical/Civil | Complete | 0 | Yes | Yes | E-102-proposed-electrical-civil-plan.pdf | 2026-06-10 | Proposed duct bank route from TX-01 to PB-01 to SE-01
E-201 | Plan and Profile Drawing | Civil/Electrical | Complete | 0 | Yes | Yes | E-201-plan-profile-drawing.pdf | 2026-06-10 | Stationing, profile, duct depth, utility crossing
E-301 | Single-Line Diagram | Electrical | Complete | 0 | Yes | Yes | E-301-single-line-diagram.pdf | 2026-06-10 | Utility source, transformer, meter, disconnect, panel, load
E-401 | Construction Details and Notes | Electrical/Civil | Complete | 0 | Yes | Yes | E-401-construction-details-notes.pdf | 2026-06-10 | Duct bank detail, pull box detail, material summary

## Action Log
Project Action Log
Action ID | Task | Category | Owner | Priority | Status | Due Date | Notes
A-001 | Create MicroStation DGN and sheet models | Drawing Setup | VA | High | Complete | 2026-06-10 | Created E-000 through E-401 sheet models
A-002 | Create drawing levels | Drawing Setup | VA | High | Complete | 2026-06-10 | Created existing, proposed, text, border, and title block levels
A-003 | Complete E-000 cover sheet | Drawing Package | VA | High | Complete | 2026-06-10 | Cover sheet and drawing index completed
A-004 | Complete E-101 existing conditions plan | Drawing Package | VA | High | Complete | 2026-06-10 | Existing site layout completed
A-005 | Complete E-102 proposed electrical-civil plan | Drawing Package | VA | High | Complete | 2026-06-10 | Proposed duct bank route completed
A-006 | Complete E-301 single-line diagram | Drawing Package | VA | Medium | Complete | 2026-06-10 | Electrical single-line completed
A-007 | Complete E-201 plan/profile drawing | Drawing Package | VA | Medium | Complete | 2026-06-10 | Profile and stationing completed
A-008 | Complete E-401 construction details | Drawing Package | VA | Medium | Complete | 2026-06-10 | Construction detail sheet completed
A-009 | Build voltage drop workbook | Calculations | VA | High | Complete | 2026-06-10 | Voltage drop, cable pull review, and quantity takeoff completed
A-010 | Create field verification checklist | Field Review | VA | Medium | Not Started | 2026-06-11 | Next deliverable
A-011 | Update README with screenshots | Documentation | VA | High | Not Started | 2026-06-11 | Add exported PDF screenshots and project explanation
A-012 | Push final project to GitHub | Documentation | VA | High | Not Started | 2026-06-11 | Final portfolio upload

## Project Schedule
Project Schedule
Phase | Deliverable | Start Date | Target Date | Status | Notes
1 | Project folder setup | 2026-06-10 | 2026-06-10 | Complete | Folder structure, README, references, drawings, calculations
2 | MicroStation drawing setup | 2026-06-10 | 2026-06-10 | Complete | Levels, DGN file, sheet models
3 | E-000 Cover Sheet | 2026-06-10 | 2026-06-10 | Complete | Cover sheet and drawing index
4 | E-101 Existing Conditions Plan | 2026-06-10 | 2026-06-10 | Complete | Site layout and existing assets
5 | E-102 Proposed Electrical-Civil Plan | 2026-06-10 | 2026-06-10 | Complete | Proposed duct bank, pull box, route lengths
6 | E-301 Single-Line Diagram | 2026-06-10 | 2026-06-10 | Complete | Electrical source-to-load diagram
7 | E-201 Plan/Profile Drawing | 2026-06-10 | 2026-06-10 | Complete | Stationing, depth, utility crossing
8 | E-401 Construction Details | 2026-06-10 | 2026-06-10 | Complete | Duct bank detail, pull box detail, quantity summary
9 | Excel calculations workbook | 2026-06-10 | 2026-06-10 | Complete | Voltage drop, cable pull review, quantity takeoff
10 | Field verification checklist | 2026-06-11 | 2026-06-11 | Not Started | Field measurement checklist
11 | README and GitHub cleanup | 2026-06-11 | 2026-06-11 | Not Started | Final documentation and upload